## Task Breakdown
Tasks |  |  | Difficulty Rating |  |  |  | Assigned | Sprint | State | Comments
|  |  | Chris | Jeff | Satchee | Average
Documentation | HLDD | Overview | 1 | 1 | 1 | 1 | Chris | 1 | TRUE
Documentation | HLDD | Notable Features / Uniqueness | 1 | 1 | 1 | 1 | Chris | 1 | TRUE
Documentation | HLDD | Target Market | 1 | 1 | 1 | 1 | Chris | 1 | TRUE
Documentation | HLDD | Game Requirements | 1 | 1 | 1 | 1 | Chris | 1 | TRUE
Documentation | HLDD | One Minute Gameplay | 1 | 1 | 1 | 1 | Chris | 1 | TRUE
Documentation | HLDD | Visual Aesthetic | 1 | 1 | 1 | 1 | Chris | 1 | TRUE
Documentation | HLDD | Risks & Challenges | 1 | 1 | 1 | 1 | Chris | 1 | TRUE
Documentation | GDD | Mission Statement | 1 | 1 | 1 | 1 | Jeff | 1 | TRUE
Documentation | GDD | Genre | 1 | 1 | 1 | 1 | Jeff | 1 | TRUE
Documentation | GDD | Platforms | 1 | 1 | 1 | 1 | Jeff | 1 | TRUE
Documentation | GDD | Game Lore | 1 | 1 | 1 | 1 | Jeff | 1 | TRUE
Documentation | GDD | Gameplay Overview | 1 | 1 | 1 | 1 | Jeff | 1 | TRUE
Documentation | GDD | Player Experience | 1 | 1 | 1 | 1 | Jeff | 1 | TRUE
Documentation | GDD | Game Objectives & Rewards | 1 | 1 | 1 | 1 | Jeff | 2 | TRUE | Started Work in Sprint 1
Documentation | GDD | Mechanics | 1 | 1 | 1 | 1 | Chris | 1 | TRUE
Documentation | GDD | Setup | 1 | 1 | 1 | 1 | Jeff | 1 | TRUE
Documentation | GDD | User Interface | 1 | 1 | 1 | 1 | Chris | 1 | TRUE
Documentation | GDD | Character Design | 1 | 1 | 1 | 1 | Jeff | 1 | TRUE
Documentation | GDD | Level Design | 1 | 1 | 1 | 1 | Chris | 1 | TRUE
Documentation | GDD | Project Management | 1 | 1 | 1 | 1 | Jeff | 1 | TRUE
Documentation | Risk Management | Methodology / Policies | 1 | 1 | 1 | 1 | Jeff | 1 | TRUE
Documentation | Risk Management | Risks | 1 | 1 | 1 | 1 | Jeff | 1 | TRUE
Documentation | Risk Management | Solutions | 1 | 1 | 1 | 1 | Jeff | 1 | TRUE
Documentation | TDD | Overview/Scope | 1 | 1 | 1 | 1 | Satchee | 1 | TRUE
Documentation | TDD | Deliverables | 1 | 1 | 1 | 1 | Satchee | 1 | TRUE
Documentation | TDD | Tools & Specification | 1 | 1 | 1 | 1 | Satchee | 1 | TRUE
Documentation | TDD | Functions and Structure | 1 | 1 | 1 | 1 | Satchee | 1 | TRUE
Documentation | TDD | UML Class diagram | 3 | 5 | 3 | 4 | Satchee | 1 | TRUE
Documentation | TDD | UML Case Diagram | 3 | 4 | 3 | 4 | Satchee | 2 | TRUE | Started Work in Sprint 1
Documentation | TDD | Project Timeline | 1 | 2 | 2 | 2 | Chris | 1 | TRUE
Documentation | TDD | Challenges | 1 | 2 | 1 | 2 | Satchee | 1 | TRUE
Documentation | Business Plan | Vision | 2 | 2 | 2 | 2 | All | 1 | TRUE
Documentation | Business Plan | Income & Expenses | 3 | 2 | 3 | 3 | Chris | 1 | TRUE
Documentation | Business Plan | Marketing | 3 | 2 | 2 | 3 | Jeff | 1 | TRUE
Documentation | Business Plan | Legalities | 1 | 2 | 2 | 2 | Satchee | 1 | TRUE
Design | Levels | Concepting | 4 | 8 | 4 | 6 | Jeff | 2 | TRUE
Design | Levels | Greyboxing | 4 | 7 | 5 | 6 | Chris | 3 | TRUE
Design | Levels | Populating | 3 | 5 | 4 | 4 | Jeff | 5 | TRUE
Design | Levels | Hiding Spots | 2 | 5 | 4 | 4 | Jeff | 2 | TRUE
Design | Levels | Plant Room Entry Points | 2 | 4 | 3 | 3 | Chris | 5 | TRUE
Design | Levels | Events | 2 | 6 | 4 | 4 | Chris & Jeff | 7 | TRUE | Started Work in Sprint 6
Design | Levels | Lighting | 6 | 5 | 5 | 6 | Chris & Jeff | 10 | TRUE | Started Work in Sprint 9
Design | Levels | Effects | 3 | 5 | 5 | 5 | Jeff | 3 | TRUE
Design | Levels | Finalised | 6 | 8 | 6 | 7 | Chris | 9 | TRUE
Design | Puzzles & Tasks | Concepting | 5 | 8 | 6 | 7 | Chris & Jeff | 3 | TRUE | Started Work in Sprint 2
Design | Puzzles & Tasks | Draft Attempts | 3 | 8 | 5 | - | Chris & Jeff |  | FALSE | Redundant Task
Design | Assets | Environment Props | 5 | 8 | 4 | 6 | Chris & Jeff | 4 | TRUE
Design | Assets | Plant Model | 4 | 8 | 6 | 6 | Chris | 3 | TRUE | Started Work in Sprint 2
Design | Assets | Asset Texture Variations (If Possible) | 3 | 5 | 6 | - | Chris & Jeff | 7 | FALSE | Not a necessary Task
Design | Player | Movement | 2 | 3 | 6 | - |  |  | FALSE | Not a necessary Task
Design | Player | Animations | 3 | 5 | 5 | 5 | Jeff | 6 | TRUE
Design | Plant Monster | Behaviours | 4 | 4 | 5 | 5 | All | 3 | TRUE
Design | Plant Monster | Texturing | 3 | 4 | 5 | 4 | Chris | 5 | TRUE | Started Work in Sprint 4
Design | Plant Monster | Animations | 5 | 7 | 4 | 6 | Chris | 10 | TRUE | Started Work in Sprint 9
Design | Plant Monster | Jumpscares | 3 | 4 | 3 | 4 | Chris & Jeff | 6 | TRUE
Design | Audio | Music | 1 | 2 | 2 | 2 | Jeff | 9 | TRUE | Worked on by Audio Students (Placeholders gatherd by Us)
Design | Audio | Ambience | 1 | 2 | 2 | 2 | Jeff | 8 | TRUE | Worked on by Audio Students (Placeholders gatherd by Us)
Design | Audio | Plant Monster | 2 | 2 | 2 | 2 | Jeff | 9 | TRUE | Worked on by Audio Students (Placeholders gatherd by Us)
Design | Audio | Player | 1 | 2 | 2 | 2 | Jeff | 9 | TRUE | Worked on by Audio Students (Placeholders gatherd by Us)
Design | Audio | SFX | 2 | 4 | 2 | 3 | Jeff | 9 | TRUE | Worked on by Audio Students (Placeholders gatherd by Us)
Design | Audio | Audio Events | 2 | 3 | 3 | 3 | Jeff | 8 | TRUE | Worked on by Audio Students (Placeholders gatherd by Us)
Design | Story/Narrative | Concepting | 5 | 7 | 4 | 6 | Chris & Jeff | 5 | TRUE | Started Work in Sprint 4
Design | Story/Narrative | Scripting | 4 | 7 | 5 | 6 | Chris & Jeff | 8 | TRUE
Design | Story/Narrative | Implementation | 3 | 5 | 4 | 4 | Chris & Jeff | 9 | TRUE
Design | UI | Menu Design | 2 | 3 | 2 | 3 | Jeff | 3 | TRUE
Design | UI | Player UI Design | 2 | 3 | 3 | 3 | Chris | 4 | TRUE
Design | UI | Menu Asset Creation | 2 | 3 | 3 | 3 | Jeff | 3 | TRUE
Design | UI | Player UI Asset Creation | 2 | 3 | 3 | 3 | Chris | 5 | TRUE
Programming | Player | Controller / Movement | 3 | 3 | 2 | 3 | Satchee | 1 | TRUE
Programming | Player | Flashlight | 2 | 4 | 3 | 3 | Chris | 7 | TRUE
Programming | Player | Camera Control | 3 | 3 | 2 | 3 | Satchee | 1 | TRUE
Programming | Player | Animations | 4 | 5 | 4 | 5 | Jeff | 6 | TRUE
Programming | AI | Pathfinding | 7 | 9 | 7 | 8 | Satchee | 5 | TRUE | Started Work in Sprint 4
Programming | AI | State Machine Core | 5 | 5 | 5 | 5 | Satchee | 4 | TRUE
Programming | AI | Roaming State | 3 | 5 | 4 | 4 | Satchee | 5 | TRUE
Programming | AI | Enter / Search Room State | 5 | 5 | 7 | 6 | Satchee | 8 | TRUE
Programming | AI | Chase Sate | 3 | 5 | 5 | 5 | Satchee | 6 | TRUE
Programming | AI | Capture State | 3 | 5 | 3 | 4 | Satchee | 6 | TRUE
Programming | AI | Animations | 4 | 4 | 4 | 4 | Chris | 7 | TRUE
Programming |  | Interactible Shader | 6 | 8 | 6 | 7 | Satchee | 9 | TRUE
Programming | UI Scripting | Main Menu | 1 | 2 | 2 | 2 | Jeff | 3 | TRUE
Programming | UI Scripting | Settings Menu | 2 | 2 | 2 | 2 | Chris | 8 | TRUE
Programming | UI Scripting | Pause Menu | 2 | 1 | 1 | 2 | Jeff | 3 | TRUE
Programming | UI Scripting | Player UI | 2 | 3 | 3 | 3 | Chris | 5 | TRUE
Programming | UI Scripting | Subtitle System | 3 | 3 | 3 | 3 | Chris | 4 | TRUE
Programming | Game Manager | Item Pickup | 3 | 3 | 2 | 3 | Satchee | 3 | TRUE
Programming | Game Manager | Using Item | 3 | 3 | 3 | - | Satchee | 3 | FALSE | Redundant, broken down into seperate tasks under tasks & puzzles
Programming | Game Manager | Inventory System/Management | 2 | 4 | 3 | 3 | Satchee | 4 | TRUE
Programming | Game Manager | Triggering Jumpsare | 2 | 1 | 2 | 2 | Jeff | 5 | TRUE
Programming | Game Manager | Objective System | 3 | 3 | 3 | 3 | Chris | 8 | TRUE
Programming | Game Manager | Game Ending (Good/Bad) | 3 | 1 | 3 | 3 | Satchee | 8 | TRUE
Programming | Puzzles & Tasks | Puzzle/Tasks Core System | 5 | 4 | 5 | 5 | Satchee | 3 | TRUE
Programming | Puzzles & Tasks | Dispay required item | 2 | 2 | 2 | 2 | Satchee | 8 | TRUE
Programming | Puzzles & Tasks | Make Barricades | 2 | 3 | 3 | 3 | Satchee & Chris | 6 | TRUE | Started Work in Sprint 5
Programming | Puzzles & Tasks | Gasoline Task | 2 | 3 | 2 | 3 | Jeff | 6 | TRUE
Programming | Puzzles & Tasks | Lock Doors | 2 | 2 | 2 | 2 | Chris | 5 | TRUE
Programming | Puzzles & Tasks | Safe Puzzle | 2 | 2 | 3 | 3 | Chris | 6 | TRUE
Programming | Puzzles & Tasks | Fireplace Puzzle | 3 | 4 | 3 | 4 | Jeff | 7 | TRUE | Started Work in Sprint 5
Programming | Puzzles & Tasks | Tape Puzzle | 2 | 4 | 3 | 3 | Chris | 6 | TRUE
Programming | Puzzles & Tasks | PC Puzzle | 3 | 3 | 4 | 4 | Satchee | 7 | TRUE | Started Work in Sprint 6
Programming | Environment | Scripted Events | 2 | 2 | 3 | 3 | Jeff | 8 | TRUE
Programming | Environment | Open Closing Doors | 1 | 2 | 2 | 2 | Satchee | 3 | TRUE | Started Work in Sprint 3
Programming | Environment | Cutscene Manager | 3 | 3 | 3 | 3 | Satchee | 7 | TRUE
Programming | Environment | Hiding Mechanic | 2 | 6 | 2 | 4 | Satchee | 3 | TRUE
Programming | API |  | ;-; | :) | :( | - |  |  | FALSE | Not included in the project
Programming | Tools | Batch Renaming | 2 | 6 | 1 | 3 | Satchee | 2 | TRUE
Programming | Tools | Hiding Objects in Inspector | 2 | 4 | 2 | 3 | Satchee | 2 | TRUE
Polishing | Adjustments | Darken Scene Lighting | 1 |  |  | 1 | Chris & Jeff | 10 | TRUE
Polishing | Adjustments | Make Flashlight Last Longer | 1 |  |  | 1 | Chris | 10 | TRUE
Polishing | Adjustments | Interact Reticle Size/Color (Increase & Change) | 1 |  |  | 1 | Chris | 10 | TRUE
Polishing | Adjustments | Make Jumpscares more reactive | 1 |  |  | 1 | Chris | 10 | TRUE
Polishing | Adjustments | Plant & Player Speed | 1 |  |  | 1 | Chris | 10 | TRUE
Polishing | Adjustments | Slow Speed while dialog plays | 1 |  |  | 1 | Chris | 10 | TRUE
Polishing | Adjustments | Different Key to drop items | 1 |  |  | 1 | Chris | 10 | TRUE
Polishing | Adjustments | Remove Jumping | 1 |  |  | 1 | Satchee | 10 | TRUE
Polishing | Adjustments | Trigger for Fireplace puzzle to collider | 1 |  |  | 1 | Chris | 10 | TRUE
Polishing | Adjustments | Clarify Objective Texts | 1 |  |  | 1 | Chris | 10 | TRUE
Polishing | Adjustments | Plant Around Corner Sequence (increase speed) | 1 |  |  | 1 | Chris | 10 | TRUE
Polishing | Adjustments | Player Height | 1 |  |  | 1 | Satchee | 10 | FALSE
Polishing | Adjustments | Sprint Animation playing while not moving | 1 |  |  | 1 | Jeff | 10 | TRUE
Polishing | Bugs / Issues | Plant Walking Through Walls (Obstacle Avoidance) | 1 |  |  | 1 | Satchee | 10 | FALSE
Polishing | Bugs / Issues | Items not working after dropping | 1 |  |  | 1 | Satchee | 10 | TRUE
Polishing | Bugs / Issues | Safe being done early/without entering code | 1 |  |  | 1 | Chris | 10 | TRUE
Polishing | Bugs / Issues | Player walking on items | 1 |  |  | 1 | Satchee | 10 | TRUE
Polishing | Bugs / Issues | Player going through Ceiling (Jumping on Bed) | 1 |  |  | 1 | Satchee | 10 | TRUE
Polishing | Bugs / Issues | Slot Selection Spam | 1 |  |  | 1 | Chris | 10 | TRUE
Polishing | Bugs / Issues | Settings not Hiding when Esc pressed | 1 |  |  | 1 | Chris | 10 | TRUE
Polishing | Bugs / Issues | Items dropping through walls/floor | 1 |  |  | 1 | Satchee | 10 | FALSE
Polishing | Additions/Finalisations | Add Batteries | 1 |  |  | 1 | Jeff | 10 | TRUE
Polishing | Additions/Finalisations | Objective Pop Ups | 1 |  |  | 1 | Chris | 10 | TRUE
Polishing | Additions/Finalisations | Interact Key Prompt | 1 |  |  | 1 | Chris | 10 | TRUE
Polishing | Additions/Finalisations | Reflection Probes | 1 |  |  | 1 | Chris | 10 | FALSE
Polishing | Additions/Finalisations | Final Audio for everything | 1 |  |  | 1 | Jeff | 10 | TRUE
Polishing | Additions/Finalisations | Computer Puzzle & Minigame | 1 |  |  | 1 | Satchee | 10 | FALSE
Polishing | Additions/Finalisations | Outside Terrain Finalized | 1 |  |  | 1 | Jeff | 10 | TRUE
Polishing | Additions/Finalisations | Final Populating for all rooms | 1 |  |  | 1 | Jeff | 10 | FALSE
Polishing | Additions/Finalisations | Player Capture Jumpscare & Comments | 1 |  |  | 1 | Chris | 10 | TRUE
Polishing | Additions/Finalisations | Ending Sequence (Cutscene / Transition) | 1 |  |  | 1 | Chris | 10 | TRUE

## Points
Total Pts | Agv./Week | Weekly Goal | Point Completion | [6 empty] | Initial Estimates
340 | 34 | 35 | Sprint | Planned Points | Points Completed | Outstanding | Completed Weekly Average | Estimated Outstanding (Weekly Avg.) | Estimated Outstanding (Weekly Goal) | I - Estimated Outstanding (Weekly Avg.) | I - Estimated Outstanding (Weekly Goal)
[6 empty] | 284 | 0 | 340 | 340 | 284 | 284
Remaining |  |  | 1 | 52 | 50 | 251 | 33 | 306 | 305 | 256 | 249
6 |  |  | 2 | 36 | 21 | 230 | 33 | 272 | 270 | 228 | 214
|  |  | 3 | 52 | 53 | 177 | 33 | 238 | 235 | 200 | 179
Total Points |  | Addrd Points | 4 | 38 | 20 | 173 | 33 | 204 | 200 | 172 | 144
Initial | 284 | 0 | 5 | 46 | 39 | 134 | 33 | 170 | 165 | 144 | 109
Sprint 1 | 301 | 17 | 6 | 47 | 35 | 99 | 33 | 136 | 130 | 116 | 74
Sprint 2 | 301 | 0 | 7 | 35 | 22 | 72 | 33 | 102 | 95 | 88 | 39
Sprint 3 | 301 | 0 | 8 | 37 | 30 | 39 | 33 | 68 | 60 | 60 | 4
Sprint 4 | 317 | 16 | 9 | 39 | 27 | 12 | 33 | 34 | 25 | 32 | 0
Sprint 5 | 317 | 0 | 10 | 43 | 37 | 6 | 33 | 0 | 0 | 4 | 0
Sprint 6 | 317 | 0
Sprint 7 | 312 | -5
Sprint 8 | 309 | -3
Sprint 9 | 309 | 0
Sprint 10 | 340 | 31